## MSFT
Sl No | Activity | Description | Status | Remarks | Start Date | End Date | Responsible
1 | Old MSAT DBs to Cloud | Identify the current Read Only Msat DBs and move them to cloud storage | Initiated | Send details to Rahul and get the cost | 2016-11-17 |  | Sarita
2 | ARTS App and DB Movement | Currently hosted on TIM infra. To move to CIO infra | WIP |  |  |  | Sarita
3 | Vchannel | EOSL server, to move to CIO infra. Under testing by development team | WIP | Put on two nodes. To test by changing the local host entry |  |  | Tejesh
4 | Inventory Update | Update the excel. Include the details of the clusters (to be taken fromIsaac) | Closed |  | 2016-11-22 | 2016-11-24 | Uday
5 | Release EOSL VMs | [5 empty] | Sysadmin PLs
6 | tickets for all sysadm activities | [5 empty] | Sysadmin PLs
7 | 10.10.1.70, 10.10.10.72, 10.10.1.120 | releasing/stopping |  |  |  |  | Sysadmin PLs
8 | careersUAT to new server | [5 empty] | Saritha
9 | Presenza schedulers issue | [5 empty] | Congrid
10 | SHINE and XI Backup tapes and CDs | Gayathri sent mail on this and to move to TIM DC | Initiated | Sent details to Vara and Nagaraju Malempati | 2016-11-24 |  | Lavanya/Gayathri

## SharePoint
Sl No | Activity | Description | Status | Remarks | Start Date | End Date | Responsible
| Corp Website to Pune | Moving Corpwebsite to Pune to supported hardware | WIP |  |  |  | Harshad/Suhail/Swati
| MB+ Dev Azure to On Prem |  | WIP |  |  |  | harshad/Suhail
| MB+ UAT Azure to On Prem | VMs request raised. Once VMs are provisioned, to do SP, VS and SQL setup | Initiated |  | 2016-11-15 |  | harshad/Suhail
| TFS Azure to On Prem | Copy code of MB+ from Azure TFS to On Prem/ Congrid complete the project folder copying. Pending with Atul for confirmation | Pending Confirmation |  |  |  | Harshad/Atul

## Hyperion and BI
Sl No | Activity | Description | Status | Remarks | Start Date | End Date | Responsible
1 | Additional RAM | Current prod cluster nodes showing high Memory Utilization. To procure additional RAM for these at the earliest | WIP | PR 0000111183 Raisd by Deva on 21st Nov. I Provided inputs to PROC team. | 2016-11-18 |  | Deva/Vikram
2 | ESSBASE |  | Planned | Santosh took approvals from Busers. Planned on 27th with 2 hrs downtime window | 2016-11-23 |  | Santosh/Jismi
3 | OBIEE Admin offer | Confirmed to Dipti on offer release with U3 as band, Sanjay and Ved approved. Candidate will be joining in a month's period

## Qlik and Taxation
Sl No | Activity | Description | Status | Remarks | Start Date | End Date | Responsible
1 | Tazxation Production setup | Shared the configiration of the Production VM requirement with Vara Vikram and Deva. | Initiated | Vikram.Vara checking. Vara suggested to go with RHEL and not OEL. | 2016-11-25 |  | Lavanya
2 | Access to Predoole team | Added the IDs of Nilesh and Swapnil in admin group. The are unable to access the server. Chetan Jadhav from TIM checking | WIP |  | 2016-11-22 |  | TIM
3 | WAPT | Gayathri initiated WAPT on current QA setup for Taxation. | WIP |  | 2016-11-21 |  | Gayathri/Robert(ISG)
4 | Qlik setup | Qlik server details |  | 10.20.125.95 |  |  |  | ciot1211 added to the server

## Brijesh
Sl No | Activity | Description | Status | Remarks | Start Date | End Date | Responsible | IP | Pwd
1 | DOVE | dove.techahindra.com external publishing. Asked Himani for ISG clearance and VAPT, WAPT closure. Asked for OS so that the SSL crtificate can be taken from TIM. | WIP |  |  |  | Himani/Lavanya | 10.20.125.58 | clouduser/User1234 root/root123
2 | RAG | Sales portal | Closed |  | 2016-11-17 | 2016-11-17 | Lavanya | 10.20.125.158 | s